## Process Template
Process FMEA
FMEA Instructions
1) Identify and name the process, product or service. Identify who has responsibility, and identify the team.
2) List the item functions in column A.
3) Identify possible failure modes in column B.
4) Describe potential effect(s) of failure modes in column C.
5) Use the provided table (in the Rating Factors Tab) to identify severity in column D.
6) Identify potential causes of failure in column E. Describe these in terms of something that can be corrected or can be controlled.
7) Rate the liklihood of the identified failure casue occurring in column F. Use the provided table in the Rating Factors Tab.
8) Describe the current process controls to prevent the failure mode in column G.
9) Use the provided table (in the Ratings Factors Tab) to determine the liklihood that that failure cause will be detected.
10) The Risk Priority Number will be calculated automatically.
11) Use the RPN to identify further actions in columns J, K, and L. Once action is taken, recalculate RPN.
Item Name: |  | FMEA Team: |  |  |  | Prepared by:
[6 empty] | FMEA Date (Orig): |  |  |  | Revision #:
Process Step or Variable or Key Input | Potential Failure Mode | Potential Effect on Customer Because of Defect | SEV | Potential Causes | OCC | Current Process Controls | DET | RPN | Actions Recommended | Resp.& Target Date | Actions Taken | SEV | OCC | DET | Future RPN
What is the process step? | In what ways can the Process Step, Variable, or Key Input go wrong? (chance of not meeting requirements) | What is the impact on the Key Output Variables (customer requirements) or internal requirements? | How Severe is effect to the customer? | What causes the Key Input to go wrong? (How could the failure mode occur?) | How frequent is cause likely to Occur? | What are the existing controls that either prevent the failure mode from occurring or detect it should it occur? | How probable is Detection of cause? | Risk Priority # to rank order concerns | What are the actions for reducing the Occurrence of the cause, or improving Detection? Should have actions on high RPN's or Severity of 9 or 10. | Who's Responsible for the recommended action? What date? | What were the actions implemented? Include completion month/year. (Then recalculate resulting RPN.) | Future Severity | Future Occurance | Future Detection

## Process Example
Process FMEA
FMEA Instructions
1) Identify and name the process, product or service. Identify who has responsibility, and identify the team.
2) List the item functions in column A.
3) Identify possible failure modes in column B.
4) Describe potential effect(s) of failure modes in column C.
5) Use the provided table (in the Rating Factors Tab) to identify severity in column D.
6) Identify potential causes of failure in column E. Describe these in terms of something that can be corrected or can be controlled.
7) Rate the liklihood of the identified failure casue occurring in column F. Use the provided table in the Rating Factors Tab.
8) Describe the current process controls to prevent the failure mode in column G.
9) Use the provided table (in the Ratings Factors Tab) to determine the liklihood that that failure cause will be detected.
10) The Risk Priority Number will be calculated automatically.
11) Use the RPN to identify further actions in columns J, K, and L. Once action is taken, recalculate RPN.
Item Name: |  | FMEA Team: |  |  |  | Prepared by:
[6 empty] | FMEA Date (Orig): |  |  |  | Revision #:
Process Step or Variable or Key Input | Potential Failure Mode | Potential Effect on Customer Because of Defect | SEV | Potential Causes | OCC | Current Process Controls | DET | RPN | Actions Recommended | Resp.& Target Date | Actions Taken | SEV | OCC | DET | Future RPN
What is the process step? | In what ways can the Process Step, Variable, or Key Input go wrong? (chance of not meeting requirements) | What is the impact on the Key Output Variables (customer requirements) or internal requirements? | How Severe is effect to the customer? | What causes the Key Input to go wrong? (How could the failure mode occur?) | How frequent is cause likely to Occur? | What are the existing controls that either prevent the failure mode from occurring or detect it should it occur? | How probable is Detection of cause? | Risk Priority # to rank order concerns | What are the actions for reducing the Occurrence of the cause, or improving Detection? Should have actions on high RPN's or Severity of 9 or 10. | Who's Responsible for the recommended action? What date? | What were the actions implemented? Include completion month/year. (Then recalculate resulting RPN.) | Future Severity | Future Occurance | Future Detection
Customer Application | Checks Being Printed Incorrectly | Checks Have To Be Re-Issued | 6 | Incorrect Information On Application Form | 4 | Check of Application Form for Correct Information by Data Enty Operator | 8 | 192 | Clerk Reviews information with customer | Clerk Manager | Completed | 8 | 2 | 4 | 64
Data Entry | Checks Being Printed Incorrectly | Checks Have To Be Re-Issued |  | Data Entry Error
Data Entry | Checks Being Printed Incorrectly | Checks Have To Be Re-Issued |  | Information Entered in Wrong Field on Application Form

## Design Template
Design FMEA
FMEA Instructions
1) Identify and name the process, product or service. Identify who has responsibility, and identify the team.
2) List the item functions in column A.
3) Identify possible failure modes in column B.
4) Describe potential effect(s) of failure modes in column C.
5) Use the provided table (in the Rating Factors Tab) to identify severity in column D.
6) Identify potential causes of failure in column E. Describe these in terms of something that can be corrected or can be controlled.
7) Rate the liklihood of the identified failure casue occurring in column F. Use the provided table in the Rating Factors Tab.
8) Describe the current process controls to prevent the failure mode in column G.
9) Use the provided table (in the Ratings Factors Tab) to determine the liklihood that that failure cause will be detected.
10) The Risk Priority Number will be calculated automatically.
11) Use the RPN to identify further actions in columns J, K, and L. Once action is taken, recalculate RPN.
Item Name: |  | FMEA Team: |  |  |  | Prepared by:
[6 empty] | FMEA Date (Orig): |  |  |  | Revision #:
Item Function | Potential Failure Mode | Potential Effect on Customer Because of Defect | SEV | Potential Causes | OCC | Current Process Controls | DET | RPN | Actions Recommended | Resp.& Target Date | Actions Taken | SEV | OCC | DET | Future RPN
What is the component, function, or feature? | In what ways can the Component, Subsystem or System potentially fail to meet the Design Intent ? | What is the impact on the Key Output Variables (customer requirements) or internal requirements? | How Severe is effect to the customer? | List every conceivable failure and/or failure mechanism for each failure mode | How frequent is cause likely to Occur? | What are the Existing Controls & Procedures (Fail-Safe, Tests, Mathemat.Calcs)that prevent either the cause or the failure mode | How probable is Detection of cause? | Risk Priority # to rank order concerns | What are the actions for reducing the Occurrence of the cause, or improving Detection? Should have actions on high RPN's or EASY FIXES | Who's Responsible for the recommended action? What date? | What were the actions implemented? Include completion month/year. (Then recalculate resulting RPN.) | Future Severity | Future Occurance | Future Detection | Future RPN

## Rating Factors
Design and Process FMEA Rating Factors
RATING | DEGREE OF SEVERITY | PROBABILITY OF OCCURRENCE |  |  | ABILITY TO DETECT
|  |  | FREQUENCY ( 1 in … ) | Cpk |  | Detection Certainty
1 | Customer will not notice the adverse effect or it is insignificant | Likelihood of occurrence is remote | 1000000 | > 1.67 | Sure that the potential failure will be found or prevented before reaching the next customer | 100%
2 | Customer will probably experience slight annoyance | Low failure rate with supporting documentation | 20000 | 1.33 | Almost certain that the potential failure will be found or prevented before reaching the next customer | 99%
3 | Customer will experience annoyance due to the slight degradation of performance | Low failure rate without supporting documentation | 5000 | approx. 1.0 | Low likelihood that the potential failure will reach the next customer undetected | 95
4 | Customer dissatisfaction due to reduced performance | Occasional failures | 2000 | < 1.0 | Controls may detect or prevent the potential failure from reaching the next customer | 90
5 | Customer is made uncomfortable or their productivity is reduced by the continued degradation of the effect | Relatively moderate failure rate with supporting documentation | 500 |  | Moderate likelihood that the potential failure will reach the next customer | 85
6 | Warranty repair or significant manufacturing or assembly complaint | Moderate failure rate without supporting documentation | 100 |  | Controls are unlikely to detect or prevent the potential failure from reaching the next customer | 80
7 | High degree of customer dissatisfaction due to component failure without complete loss of function. Productivity impacted by high scrap or rework levels. | Relatively high failure rate with supporting documentation | 50 |  | Poor likelihood that the potential failure will be detected or prevented before reaching the next customer | 70
8 | Very high degree of dissatisfaction due to the loss of function without a negative impact on safety or governmental regulations | High failure rate without supporting documentation | 20 |  | Very poor likelihood that the potential failure will be detected or prevented before reaching the next customer | 60
9 | Customer endangered due to the adverse effect on safe system performance with warning before failure or violation of governmental regulations | Failure is almost certain based on warranty data or significant Design Verification* testing | 10 |  | Current controls probably will not even detect the potential failure | 50
10 | Customer endangered due to the adverse effect on safe system performance without warning before failure or violation of governmental regulations | Assured of failure based on warranty data or significant Design Verification* testing | 2 |  | Absolute certainty that the current controls will not detect the potential failure | < 50
*Design Verification Testing (DVT): Test conducted when designing new products/services to verify that the optimal process design performs at the level specified by customer requirements (CTQs). DVT is a methodical approach used to identify and resolve problems before finalizing the process for new products/services.